## Instructions
Saadiyat Lagoons HSE Scoring Template - Google Form Ready
Use Weekly_Inspections as the response/master record after upload to Google Sheets. Users should complete only visible columns; hidden columns and dashboards update automatically.
2. Complete the visible input columns only. Hidden columns calculate automatically.
3. Score each KPI from 0 to 5. 0 = collapse of control, 5 = excellent sustained control.
4. Package and Cluster are mandatory. Contractor and responsible team auto-populate.
5. Weekly_Dashboard is for top management review. Monthly_Dashboard tracks recognition trend.
6. Gap_Analysis and CAPA_Tracker are for close-out management.

## Cluster_Master
Cluster Master Register
Reference data used for package/cluster selection and automatic population of contractor and leadership accountability details.
Package | Cluster | Contractor | Project Director (PD) | Project Manager (PM) | Construction Manager (CM) | HSE Manager (HSEM) | Section Engineer (SE)
2 | Cluster 7A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat
2 | Cluster 7B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Eyad
2 | Cluster 8A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel
2 | Cluster 8B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel
2 | Cluster 8C | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel
2 | Cluster 8D | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel
3 | Cluster 3 | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani
3 | Cluster 4 | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani
3 | Cluster 5 | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani
3 | Cluster 6 | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani
4 | Cluster 1A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Alaa Hegab | Timur Terakopov | Amr Taha
4 | Cluster 1B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Hossam Ali Maher | Timur Terakopov | Md Ramadan / Osama Said
4 | Cluster 2A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa
4 | Cluster 2B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa
4 | Cluster 2C | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef

## KPI_Weights
KPI Weights and Gate Rules
Weights sum to 100%. Critical gate KPIs trigger a red flag if scored 0 or 1 in any inspection.
KPI | Weight | Critical Gate KPI? | Notes
Work at Height Control | 12% | YES | Primary fall prevention and work at height control
Edge Protection | 12% | NO | Continuity and quality of edge protection
Falling Object Prevention | 5% | NO | Exclusion zones, toe boards, debris/tool control
Excavation Safety | 8% | YES | Barricading, access, services, support, spoil setback
Scaffolding Compliance | 10% | YES | Tagging, inspection, full planking, access, stability
PTW Implementation | 8% | YES | Valid PTW, correct scope, signatories, controls
PTW Field Verification | 6% | NO | Physical field verification before permit approval
MSRA Quality | 3% | NO | Task-specific risk assessment and understanding
Lifting/Precast Installation | 10% | YES | Lift plan, appointed person, exclusion, rigging
Traffic & Man-Machine Interface | 6% | NO | Pedestrian segregation, routes, signage, reversing
Housekeeping/Waste Management | 3% | NO | Cleanliness, stacking, access routes, slip/trip control
Welfare Arrangement | 3% | NO | Segregation, storage, transfer/disposal control
Fire Readiness | 5% | NO | Fire points, extinguishers, hot work readiness
Supervision & Subcontractor Control | 3% | NO | Visible supervision and subcontractor control
Temporary Electrical & Tool Safety | 6% | NO | Temporary power, RCD, condition of tools/cables
Total | 100%

## Lookups
Lookup Lists | [7 empty] | Score_List
Lists used for dropdowns in the Weekly_Inspections and CAPA_Tracker sheets. | [7 empty] | 0
Package_List | Cluster_List | Evaluator_Role_List | High_Risk_Activity_List | Yes_No_List | Root_Cause_List | Status_List | KPI_List | 1
2 | Cluster 7A | Project Director | Work at Height | YES | Leadership failure | Open | Work at Height Control | 2
3 | Cluster 7B | Project Manager | Edge Protection | NO | Poor supervision | In Progress | Edge Protection | 3
4 | Cluster 8A | Construction Manager | Falling Objects |  | Poor planning | Closed | Falling Object Prevention | 4
| Cluster 8B | HSE Manager | Excavation |  | PTW failure | On Hold | Excavation Safety | 5
| Cluster 8C | Section Engineer | Scaffolding |  | Weak MSRA |  | Scaffolding Compliance
| Cluster 8D | QA/QC | Permit to Work |  | Poor subcontractor control |  | PTW Implementation
| Cluster 3 | KEO | MSRA / Risk Assessment |  | Resource constraint |  | PTW Field Verification
| Cluster 4 | Client | Lifting Operations |  | Inadequate competence |  | MSRA Quality
| Cluster 5 | Other | Traffic Management |  | Poor housekeeping culture |  | Lifting Operations
| Cluster 6 |  | Housekeeping |  | Interface / simultaneous activity conflict |  | Traffic & Man-Machine Interface
| Cluster 1A |  | Waste Management |  | Other |  | Housekeeping Standard
| Cluster 1B |  | Fire Readiness |  |  |  | Waste Management
| Cluster 2A |  | Electrical Safety |  |  |  | Fire Readiness
| Cluster 2B |  | Portable Power Tools |  |  |  | Supervision & Subcontractor Control
| Cluster 2C |  | Heat Stress |  |  |  | Temporary Electrical & Tool Safety
Other

## Weekly_Inspections
Weekly Inspection Entry Sheet - Google Form Ready
Complete only visible fields. Use the 0-5 dropdown for each KPI. Package and Cluster auto-fill contractor leadership and the dashboard updates automatically.
Inspection_ID | Inspection_Date | Week_No | Month | Package | Cluster | Package_Cluster_Check | Contractor | Project Director (PD) | Project Manager (PM) | Construction Manager (CM) | HSE Manager (HSEM) | Section Engineer (SE) | Your_Name | Your_Role | Area_or_Villa | Workers_Observed | Main_High_Risk_Activity | Stop_Work | Work_at_Height | Edge_Protection | Falling_Object_Prevention | Excavation_Safety | Scaffolding_Compliance | PTW_Implementation | PTW_Field_Verification | MSRA_Quality | Lifting/Precast Installation | Traffic_Interface | Housekeeping/Waste Management | Welfare Arrangement | Fire_Readiness | Supervision_Subcontractor | Electrical_Tool_Safety | Total_Score | Raw_Score_% | Weighted_Score_% | Critical_Red_Flag | Award_Eligible | Rating_Band | Repeat_Issue_Seen | Likely_Root_Cause | Top_3_Gaps_Observed | Immediate_Action_Taken | Preventive_Action_Required | Positive_Observations | Action_Owner | Target_Closeout_Date | Evidence_Link_or_Photo | KPI_for_PD_Attention | KPI_for_PM_Attention | KPI_for_CM_Attention | KPI_for_HSEM_Followup | KPI_for_SE_Supervision | Leadership_Visible_Effective | Unsafe_Work_Corrected_Immediately | Best_Improved_Cluster_this_Week | Cluster_Needing_Immediate_Intervention
20260326-Cluster2C-01 | 2026-03-26 | 13 | 2026-03 | 4 | Cluster 2C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef | Godwin | KEO | Villa 8 to 16 |  | Work at Height | YES | 2 | 2 | 3 | 3 | 2 | 3 | 1 | 3 |  | 3 | 1 | 1 | 2 | 1 | 2 | 29 | 38.67% | 39% | YES | NO | Critical | YES | Leadership failure | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Unsafe work practices were suspended immediately. The CM of the cluster was called but he refused to visit the location. | 1. PTW must be controlled by the main contractor. 2. Close supervision of sub-contractors by main contractor shall be ensured. 3. Non-performing subcontractors shall not be paid and shall be removed from project. 4. Non-performing construction team shall be replaced without delays |  | 1-3rd recommendation by the cluster CM 4th recommendation by the PD. | 2026-04-02
20260326-Cluster8A-01 | 2026-03-26 | 13 | 2026-03 | 2 | Cluster 8A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Godwin | KEO | General |  | Scaffolding | NO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 59 | 78.67% | 79.4% | NO | YES | Good | NO | Other | No significant gap observed | The team was commended for their visible leadership in driving transformation at Cluster 8A. | The Construction Manager and his team were advised to ensure that sub-contractors do not mess up with their site. The following advise was given: 1. No payment for work if site condition is below the acceptable standard. 2. Close supervision of sub-contractors by the construction team of the main contractor. 3. Housekeeping shall be maintined for all shift. 4. Provide a temporary storage area for waste for each villa. 5. PTW shall remain under the control of the main contractor. |  | Construction Manager of Cluster 8A HSE Manager of TAJV | Always
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00158 | 2026-04-03 | 14 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shakir | KEO | villa 65,68 |  | Edge Protection | YES | 3 | 3 | 4 | na | 4 | 3 | 3 | 4 | 3 | 4 | 2 | 4 | 4 | 3 | 3 | 47 | 62.67% | #VALUE! | NO | NO | Needs Improvement | YES | Poor supervision | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection |  | Construction Manager Cluster 04 | 2026-04-10 | uploaded on Asite
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00159 | 2026-04-04 | 14 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shakir | KEO | cluster 05B villa 276 |  | Edge Protection | NO | 2 | 2 | 3 | 3 | 4 | 4 | 3.5 | 4 | 4 | 3 | 3 | 4 | 3 | 3 | 3 | 48.5 | 64.67% | 62.6% | NO | NO | Needs Improvement | YES | Poor subcontractor control | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection |  | Construciton manager | 2026-04-09 | Upload on Asite
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00160 | 2026-04-04 | 14 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | cluster 06 block 02 |  | Edge Protection | NO | 4 | 5 | 1 | 1 | 4 | 3 | 3 | 4 | 1 | 1 | 3 | 3 | 5 | 5 | 5 | 48 | 64% | 63.8% | YES | NO | Needs Improvement | YES | Poor supervision | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection |  | Construction Manager | 2026-04-11 | uploaded on Asite
20260403-Cluster3-01 | 2026-04-03 | 14 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shinoj M | KEO | villa 99-110 & 16 axis |  | Edge Protection | NO | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 2 | 2 | 4 | 4 | 3 | 3 | 47 | 62.67% | 62.8% | NO | NO | Needs Improvement | YES | Poor planning | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection |  | Project engineer construction manager |  | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00196 | 2026-04-02 | 14 | 2026-04 | 2 | Cluster 7A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat | Jackson | KEO | General |  | Edge Protection | YES | 3 | 3 | 1 | NA | 2.5 | 2 | 1 | 4 | 2 | 4 | 2 | 4 | 2 | 1 | 2 | 33.5 | 44.67% | #VALUE! | NO | NO | Poor | YES | Poor supervision | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | All activities inside the visited villa have been suspened and corrective and preventive actions required have been communicated with action owners . | Provide competent supervsion to ensure the activities inline with OSH requirements and proeprly managing the subcontractor. |  | Project engineer construction manager | 2026-04-09 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00161 | 2026-04-06 | 15 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shinoj M | KEO | Villa 12-17 |  | Traffic Management | NO | 3 | 2 | 3 | 3 | 4 | 2 | 3 | 3 | 3 | 1 | 4 | 4 | 3 | 3 | 3 | 44 | 58.67% | 56.8% | NO | NO | Poor | YES | Poor planning | 1. Poor coordination 2. Poor sub-contractor control 4. PTW failure | 1. Maintain the pedestrian access 2. Reinstate the barricades 3. Provide access to the villas 4.Apoint competent scaffolding crew | 1. Preplan the activities 2. Conduct a week's look-ahead planning to avoid conflicts 3. Conduct training for the involved teams 4. Evaluate the competency of the scaffolding crew |  | Construction manager Project Engineer HSE officer |  | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00197 | 2026-04-02 | 14 | 2026-04 | 2 | Cluster 7B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Eyad | Jackson | KEO | General |  | Work at Height | NO | 3.5 | 3.5 | 4 | NA | 3.5 | 4 | 2 | 4 | 3.5 | 4.5 | 5 | 4 | 3 | 4 | 3 | 51.5 | 68.67% | #VALUE! | NO | NO | Needs Improvement | YES | Poor subcontractor control | 1. Poor sub-contractor control | Cordination Meeting conducted | Sub contractor shall be managed based on the project OSH Requirements |  | Project engineer construction manager | 2026-04-09 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00198 | 2026-04-03 | 14 | 2026-04 | 2 | Cluster 8C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel | Jackson | KEO | General |  | Scaffolding | NO | 3 | 3.5 | 2.5 | 4 | 3 | 3.5 | 3.5 | 4 | 3 | 4 | 4 | 4 | 2.5 | 3 | 3.5 | 51 | 68% | 66.8% | NO | NO | Needs Improvement | YES | Inadequate competence | Inadequate comptence | Coordination Meeting conducted | Regular Training sessions shall be carried out |  |  | 2026-04-10 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00198 | 2026-04-03 | 14 | 2026-04 | 2 | Cluster 8D | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel | Jackson | KEO | General |  | Electrical Safety | NO | 3.5 | 3 | 3 | 4 | 3.5 | 3 | 3 | 4 | 3 | 4 | 3.5 | 4 | 3 | 3 | 3.5 | 51 | 68% | 67.1% | NO | NO | Needs Improvement | YES | Poor supervision | Poor supervision | Coordination Meeting conducted | Regular scaffolding and Distribution Board inspection |  |  | 2026-04-10 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00199 | 2026-04-06 | 15 | 2026-04 | 4 | Cluster 1A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Alaa Hegab | Timur Terakopov | Amr Taha | Jackson | KEO | General |  | Scaffolding | YES | 3 | 4 | 4 | 3 | 2.5 | 4 | 4 | 4 | 3 | 4 | 4 | 3.5 | 3.5 | 2.5 | 3.5 | 52.5 | 70% | 68.7% | NO | NO | Needs Improvement | YES | Poor subcontractor control | Poor subcontractor control | Unsafe work has been suspended | Regular scaffolding and Distribution Board inspection |  |  | 2026-04-12 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00200 | 2026-04-06 | 15 | 2026-04 | 4 | Cluster 1B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Hossam Ali Maher | Timur Terakopov | Md Ramadan / Osama Said | Abdel Monem | KEO | General |  | Scaffolding | NO | 4 | 4 | 4.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 3.5 | 3 | 58.5 | 78% | 78.5% | NO | YES | Good | YES | Poor subcontractor control | Poor subcontractor control | Coordination Meeting conducted | Regular scaffolding and Distribution Board inspection |  |  | 2026-04-12 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00162 | 2026-04-06 | 15 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shakir | KEO | General |  | Lifting Operations | YES | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 4 | 3 | 3 | 3 | 4 | 2 | 2 | 3 | 45 | 60% | 61.4% | NO | NO | Needs Improvement | YES | Poor supervision | • HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | • Unsafe activities were stopped immediately. • Housekeeping, waste removal, and access rectification started | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. |  | Construction manager Project Engineer | 2026-04-10 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-WR-HS-75 | 2026-04-07 | 15 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shakir | KEO | General |  | Fire Readiness | NO | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 3 | 4 | 3 | 2 | 4 | 3 | 4 | 2 | 50 | 66.67% | 69.8% | NO | NO | Need improvments | YES | PTW failure | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | unsafe blocks observed in walk fixed away from edge | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. |  | Construction manager Project Engineer | 2026-04-14 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-WR-HS-75 | 2026-04-07 | 15 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | General |  | Electrical Safety | NO | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 4 | 2 | 52 | 69.33% | 71% | NO | NO | Needs Improvement | YES | Poor subcontractor control | •HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | permit to work verification done on site.edge protection team was called to fix the edge protection and excavation barricades | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. |  | Construction Manager | 2026-04-14 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00201 | 2026-04-07 | 15 | 2026-04 | 2 | Cluster 7A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat | Jackson | KEO | General |  | Falling Objects | NO | 3.5 | 3.5 | 3.5 | 2 | 3 | 2.5 | 2.5 | 4 | 3 | 4 | 3 | 4 | 3 | 3 | 4 | 48.5 | 64.67% | 63.5% | NO | NO | Needs Improvement | YES | Poor supervision | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | edge protection team was called to fix the edge protection and excavation barricades | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs |  | Construction manager Project Engineer | 2026-04-12 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00202 | 2026-04-07 | 15 | 2026-04 | 2 | Cluster 7A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat | Jackson | KEO | General |  | Edge Protection | NO | 4 | 3.5 | 4 | 4 | 3.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 58 | 77.33% | 76.8% | NO | YES | Good | YES | Poor supervision | •HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Instructed contractor to reverify all scaffolding | Competent scaffolding inspector shall be inspected all scaffolding units |  | Construction manager Project Engineer | 2026-04-12 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00164 | 2026-04-08 | 15 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | General |  | Excavation | YES | 4 | 2 | 4 | 4 | 4 | 3 | 3 | 4 |  | 3 | 3 | 4 | 4 | 4 | 3 | 49 | 65.33% | 61.4% | YES | NO | Needs Improvement | YES | Poor supervision | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Worker removed from the villa in adequate access and edge protection | • Enforce strict supervision and permit compliance. • Implement proper planning, housekeeping, and waste management systems. • Conduct regular inspections, training, and safety awareness programs. • Access should always be well-maintained and inspected by a competent person • Permit to work should only be issued if the villa is safe to work in |  | Construction manager Project Engineer | 2026-04-15 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00163 | 2026-04-08 | 15 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shinoj M | KEO | Block 03 |  | Permit to Work | YES | 2 | 4 | 4 | 3 | 3 | 1 | 1 | 3 | 3 | 2 | 2 | 4 | 4 | 2 | 2 | 40 | 53.33% | 53.4% | YES | NO | Poor | YES | Poor subcontractor control | 1. Communication of OHS procedures 2. lack of OHS awareness in supervision level 3. Lack of monitoring | 1. Worker removed from the villa 2. safe access provided by the contractor 3. allocated people fro material arrangements | 1. Conduct training and awareness on the site supervision level 2. Conduct routine inspections 3. |  | 1. Project engineer 2. Construction Manager 3. OHS offcer |  | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00165 | 2026-04-10 | 15 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shinoj M | KEO | Block 02 &01 |  | Edge Protection | NO | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 54 | 72% | 71% | NO | NO | Needs Improvement | YES | Inadequate competence | 1. Training and awareness 2. Supervision 3. Inspection | 1. Appoint a competent team for barricading arrangements 2. Provide rebar caps fro protruding steel 3. Provide our riggers for scaffolding | 1. Competency assessment should be conducted 2. Period monitoring should be implemented 3. Preventive maintenance should be conducted |  | 1 Construction Manager 2 Project Engineer 3 HSE |  | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00166 | 2026-04-10 | 15 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 |  |  |  |  | Other | YES | 4 | 4 | 4 |  |  | 2 | 2 | 3 |  | 3 | 3 | 4 | 3 | 2 | 2 | 36 | 48% | 45% | YES | NO | Poor | YES | Poor supervision | • Lack of inspection • Inadequate supervision • PTW implementation | • Work suspended for steel fixing , inside villa with yellow or red flags • Permit suspended for all the villa with no adequat flagging system | • • Provide safe and proper access platforms (working platforms, access scaffolds, or mobile platforms) before starting rebar activities. • • Ensure ladders and stairs are of industrial grade, secured, and positioned at safe angles. • • Install temporary working platforms with guardrails where rebar work is done at height. • • Conduct Task Risk Assessment (TRA) specifically for rebar activities before work starts. • • Assign a competent supervisor to verify access arrangements daily. • • Include access requirements in the method statement and toolbox talks. • • Stop work immediately if safe access is not available. |  | Construction manager Project Engineer | 2026-04-17 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00203 | 2026-04-08 | 15 | 2026-04 | 2 | Cluster 8B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Abdul Monem | KEO | General |  | Excavation | NO | 3.5 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 48.5 | 64.67% | 65.8% | NO | NO | Needs Improvement | YES | Poor supervision | PTW Implementation Inadequate Supervison | Adivised supervsison team to adress all concerns raised by KEO |  |  | Construction manager Project Engineer | 2026-04-12 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00204 | 2026-04-08 | 15 | 2026-04 | 4 | Cluster 2B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Jackson | KEO | General |  | Work at Height | YES | 3 | 3 | 2.5 | 3 | 3 | 4 | 4 | 4 | 2.5 | 3.5 | 2 | 4 | 3.5 | 3 | 3.5 | 48.5 | 64.67% | 63.6% | NO | NO | Needs Improvement | YES | Poor supervision | Lack of inspection Inadequate Supervison | Leading edge activities which was carried out unsafely has been suspended . Instructed contractor to provide adequate edge proetction.
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00205 | 2026-04-10 | 15 | 2026-04 | 2 | Cluster 8B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Abdel Monem | KEO | General |  | Excavation | YES | 3 | 3.5 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 4 | 3.5 | 3.5 | 4 | 50.5 | 67.33% | 66.8% | NO | NO | Needs Improvement | YES | Poor supervision | Lack of inspection Inadequate Supervison | Boundry wall excavation has been suspended and corrective actions are communicated with action owners. | Close competent supervision & PTW & MSRA requirements shall be implemented |  | Construciton manager | 2026-04-13 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00206 | 2026-04-08 | 15 | 2026-04 | 2 | Cluster 8C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel | Jackson | KEO | General |  | Work at Height | YES | 2.5 | 2.5 | 3 | 3.5 | 2.5 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 3 | 2.5 | 2.5 | 46 | 61.33% | 58.7% | NO | NO | Needs Improvement | YES | Poor subcontractor control | Inadequate supervsion | Activity has been suspended and instructed contractor to verify the working platform | Close competent supervision & PTW & MSRA requirements shall be implemented |  | Construciton manager | 2026-04-11 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-WR-HS-00090 | 2026-04-02 | 14 | 2026-04 | 4 | Cluster 2A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Javed | KEO | General |  | Permit to Work | YES | 3 | 3 | 3.5 | 3 | 3 | 2 | 2 | 4 | 3 | 4 | 3.5 | 4 | 3 | 2 | 3 | 46 | 61.33% | 59.8% | NO | NO | Needs Improvement | YES | Poor subcontractor control | Inadequate supervsion Poor Planning | PTW Cancelled | Close competent supervision & PTW & MSRA requirements shall be implemented |  | Construciton manager | 2026-04-06 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00207 | 2026-04-09 | 15 | 2026-04 | 2 | Cluster 8A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Abdel Monem | KEO | General |  | Excavation | YES | 3 | 3.5 | 2.5 | 2.5 | 2.5 | 3 | 3 | 4 | 3 | 4 | 2.5 | 4 | 3 | 3 | 3.5 | 47 | 62.67% | 61.6% | NO | NO | Needs Improvement | YES | Poor supervision | Inadequate supervsion Poor Planning | Boundry wall excavation has been suspended and corrective actions are communicated with action owners. | Close competent supervision & PTW & MSRA requirements shall be implemented |  | Construciton manager | 2026-04-13 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00167 | 2026-04-11 | 15 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shinoj M | KEO | Block 01 |  | Electrical Safety | NO | 3 | 4 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 54 | 72% | 71.4% | NO | NO | Needs Improvement | YES | Poor subcontractor control | 1. PTW implementation 2 . Training and awareness 3. inspection | 1. Removed the non - inducted peolple from the site 2. Instructed to appoint a resource for access arrangements 3. Advised the engineer to allocate electricians to conduct DB inspection | 1. Pre-plan the activities to avoid SIMOS 2. Assess the adequacy of the inspection team 3. Conduct preventive maintenance |  | 1. Construction Manager 2. Project Engineer 3. OHS |  | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00168 | 2026-04-11 | 15 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shinoj M | KEO | General |  | Traffic Management | NO | 3 | 3 | 4 | 3 | 2 | 3 | 3 | 4 | 3 | 2 | 4 | 4 | 3 | 4 | 3 | 48 | 64% | 60.2% | NO | NO | Needs Improvement | YES | Poor planning | 1. Training and Awareness 2. Inadequate planning of activities 3. Inadequate supervision | 1 Removed persons from areas where inadequate access 2 instructed to provide barricades in open slab edges 3 suspended the scaffolding activities due to a lack of sequence | 1. Ensure the working platforms are in place as per the MSRA 2 Plan the activities to comply with pedestrian access 3 ensure competent supervision |  | 1. Construction Manager 2. Project Engineer 3. OHS |  | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00169 | 2026-04-13 | 16 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shinoj M | KEO | Block 01 |  | Permit to Work | YES | 3 | 3.5 | 4 | 3.5 | 2.5 | 2 | 2 | 4 | 3 | 2 | 2 | 4 | 3 | 2 | 4 | 44.5 | 59.33% | 59.2% | NO | NO | Poor | YES | Poor supervision | 1. Lack of inspections 2. Inadequate supervision 3. Competancy | 1. Suspended the activities in the affected areas 2 . Instructed the project engineer to arrange safe access to villas | Conduct training to for permit ( PTW) Ensure adequate supervisors are appointed Competency assesment |  | 1. Construction Manager 2. Project Engineer 3. OHS |  | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00170 | 2026-04-13 | 16 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shakir | KEO | Block 02 |  | Fire Readiness | YES | 4 | 3 | 3.5 | 3.5 | 3.5 | 3 | 4 | 4 |  | 3 | 3.5 | 4 | 4 | 4 | 4 | 51 | 68% | 64.2% | YES | NO | Needs Improvement | YES | Poor supervision | • Hot work activities were conducted without a fire watcher. • Smoking was observed in an undesignated area. • Materials were stored inside villas without fire sprinklers or fire extinguishers. | • Hot work was stopped, unsafe areas were barricaded, and smoking inside the villa was prohibited immediately. Fire extinguishers were provided, and corrective safety measures were instructed for immediate implementation. | • Enforce strict compliance with hot work permit procedures, including mandatory fire watcher deployment. • Establish and clearly mark designated smoking areas and prohibit smoking outside these zones. • Ensure all excavations, openings, and edges are permanently barricaded with proper signage. • Provide complete edge protection systems, including mesh and toe boards, at all elevated areas. • Restrict material storage inside villas and ensure adequate firefighting equipment is always available. • Conduct regular HSE inspections, toolbox talks, and supervisory monitoring to prevent recurrence. |  | senior Project Engineer | 2026-04-17 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00171 | 2026-04-15 | 16 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shakir | KEO | Block 02 |  | Work at Height | NO | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 4 | 3 | 55 | 73.33% | 73.6% | NO | NO | Needs Improvement |  | Poor planning | • Inadequate Edge Protection (Work at Height Risk) • Poor Traffic Management & Pedestrian Segregation • Temporary Electrical & Power Tool Safety Deficiencies | • Workers without power tool training were suspended • Pedestrian access arrangements made with a soft barrier for the time being | • Fix edge protection, walkways, and cable routes. • Use only trained and authorized workers. • Do regular safety inspections. |  | Construction Manager | 2026-04-22 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00172 | 2026-04-15 | 16 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shinoj M | KEO | Block 01 |  | Scaffolding | YES | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 4 | 3 | 48 | 64% | 63.2% | NO | NO | Needs Improvement | YES | Inadequate competence | 1. Subcontractor management 2. inspection and training 3. Housekeeping arrangements | 1 suspended the activities in the affected areas 2 instructed the engineer to provide barricades 3 Advised INNOVO to inspect the Plant and equipments | 1. Assess the competency of the execution team 2. Assess the adequacy of resources 3 Conduct routin etraining |  | 1. Construction Manager 2. Project Engineer 3. OHS |  | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00209 | 2026-04-10 | 15 | 2026-04 | 2 | Cluster 7A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat | Jackson | KEO | General |  | Work at Height | YES | 2.5 | 4 | 4 | 3.5 | 2.5 | 2.5 | 2 | 4 | 4 | 4 | 4 | 2 | 2.5 | 2.5 | 3.5 | 47.5 | 63.33% | 63.6% | NO | NO | Needs Improvement | YES | Poor subcontractor control | 1. PTW implementation 2 . Training and awareness 3. Subcontractor control | Work at height Activities have been suspended | Close competent supervsion Regular trainings |  | Construction Manager | 2026-04-15 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00208 | 2026-04-13 | 16 | 2026-04 | 2 | Cluster 8A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Abdel Monem | KEO | General |  | Excavation | YES | 3 | 3.5 | 3.5 | 2 | 3 | 2 | 2 | 4 | 3.5 | 4 | 4 | 4 | 3 | 2 | 3.5 | 47 | 62.67% | 61.3% | NO | NO | Needs Improvement | YES | Poor supervision | 1. PTW implementation 2 . Training and awareness 3. MSRA implementaion | Install proper hard barricades around the excavation area. | Close competent supervsion Regular trainings |  | Construction Manager | 2026-04-17 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00210 | 2026-04-13 | 16 | 2026-04 | 4 | Cluster 2A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Jackson | KEO | General |  | Edge Protection | YES | 2.5 | 2 | 3 | 3 | 2.5 | 2 | 2 | 3 | 3 | 3.5 | 3 | 4 | 3 | 3 | 3 | 42.5 | 56.67% | 53.8% | NO | NO | Poor | YES | Poor supervision | 1. PTW implementation 2 . Training and awareness 3. MSRA implementaion | Edge Proetctions shall be reinstated | Close competent supervsion Regular trainings |  | Construction Manager | 2026-04-17 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00211 | 2026-04-15 | 16 | 2026-04 | 4 | Cluster 2C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef | Jackson | KEO | General |  | Excavation | YES | 3.5 | 3.5 | 4 | 0 | 3.5 | 2 | 2 | 3 | 3.5 | 3 | 3.5 | 0 | 3.5 | 3.5 | 3.5 | 42 | 56% | 57.7% | YES | NO | Poor | YES | Poor supervision | 1. PTW implementation 2 . Training and awareness 3. MSRA implementaion | Install proper hard barricades around the excavation area. | A formal excavation permit-to-work system shall be strictly enforced, and excavation checklists shall be fully implemented and verified at the work location prior to and during execution of activities. |  | construction Manager | 2026-04-17 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00212 | 2026-04-15 | 16 | 2026-04 | 4 | Cluster 1A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Alaa Hegab | Timur Terakopov | Amr Taha | Abdel Monem | KEO | General |  | Excavation | NO | 3 | 3.5 | 4 | 3 | 2.5 | 3 | 3 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | 2.5 | 48.5 | 64.67% | 64.4% | NO | NO | Needs Improvement | YES | Poor supervision | 1. PTW implementation 2 . Training and awareness 3. MSRA implementaion | Install proper hard barricades around the excavation area. | Close Competent supervsion Regular trainings |  | Construction manager Project Engineer | 2026-04-18 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00173 | 2026-04-17 | 16 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | villa 65 ,66,68 |  | Excavation | YES | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 |  | 3 | 4 | 4 | 3 | 4 | 3 | 52 | 69.33% | 67% | YES | NO | Needs Improvement | YES | PTW failure | Lack of inspection • Lack of monitoring • PTW implementation | site engineer was informed to close all the open excavation and provide proper barricades | Enforce PTW requirements before starting any high‑risk activity. Maintain proper barricading, segregation, and cable protection at all times. Strictly enforce site rules, including no smoking and designated access routes. Conduct regular inspections, testing, and supervision to ensure compliance. |  | Marco , Mohammed | 2026-04-24 | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00174 | 2026-04-17 | 16 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shinoj M | KEO | vila 135 & 153 Axis |  | Permit to Work | NO | 2 | 3 | 3 | 3 | 4 | 1 | 1 | 4 | 3 | 3 | 2 | 4 | 2 | 2 | 3 | 40 | 53.33% | 53% | YES | NO | Poor |  | PTW failure | 1 Poor subcontractor control 2 Inadequate competence 3 Inspectiona and monitoring | 1 Advised the contractor to allocate adequate manpower to rectify the issues, such as barricades, manhole openings, etc | 1( conduct competance assesment of key persons 2 conduct regular trainings 3 periodic inspection shopuld be arranged |  | Construction manager HSE |  | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00219 | 2026-04-16 | 16 | 2026-04 | 4 | Cluster 2B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Godwin | KEO |  |  | Permit to Work | YES | 0 | 3 | 3 | 4 | 3 | 0 | 0 | 3 |  | 3 | 4 | 4 | 4 | 0 | 3 | 34 | 45.33% | 40.4% | YES | NO | Poor | YES | PTW failure | Lack of planning PTW failure Lack of Subcontractor control Lack of supervision No leadership presence | High risk activity was suspended and workers removed from risk area. The PM and HSE team were invited and advised to ensure PTW implementation, close supervision and control of subcontractors. | 1. Prepare Monthly lookahead programme for each package; 2. Prepare Weekly lookahead programme for each cluster; 3. Prepare Daily activity schedule for each cluster / block / villa 4. Develop Supervision deployment plan identifying the responsible site engineers, supervisors, and HSE personnel for each work front. 5. Ensure Subcontractors' engagement in the project is strictly based on the above plans. No work shall commence without an approved PTW by the main contractor. 6. Communicate officially to all subcontractors that no activity shall commence without first reporting to the main contractor on daily basis. 7. Regularly share the above plans with KEO for close follow up and monitoring. | Monthly lookahead programme for each package; | Cluster Construction Manager | 2026-04-23 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00220 | 2026-04-16 | 16 | 2026-04 | 4 | Cluster 2C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef | Godwin | KEO |  |  | Permit to Work | YES | 3 | 3 | 3 | 0 | 3 | 0 | 0 | 2 |  | 2 | 1 | 4 | 4 | 0 | 1 | 26 | 34.67% | 35.2% | YES | NO | Critical | YES | PTW failure | Lack of planning PTW failure Lack of Subcontractor control Lack of supervision No leadership presence | High risk activity was suspended and workers removed from risk area. The PM and HSE team were invited and advised to ensure PTW implementation, close supervision and control of subcontractors. | 1. Prepare Monthly lookahead programme for each package; 2. Prepare Weekly lookahead programme for each cluster; 3. Prepare Daily activity schedule for each cluster / block / villa 4. Develop Supervision deployment plan identifying the responsible site engineers, supervisors, and HSE personnel for each work front. 5. Ensure Subcontractors' engagement in the project is strictly based on the above plans. No work shall commence without an approved PTW by the main contractor. 6. Communicate officially to all subcontractors that no activity shall commence without first reporting to the main contractor on daily basis. 7. Regularly share the above plans with KEO for close follow up and monitoring. | Weekly lookahead programme for each cluster; | Cluster Construction Manager | 2026-04-23 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00213 | 2026-04-16 | 16 | 2026-04 | 2 | Cluster 8C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Ahmad Adel | Shinoj | KEO | General |  | Scaffolding | NO | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 58 | 77.33% | 77.8% | NO | YES | Good | NO | Other | Training and Awareness | working on Double height scaffoding has been suspended | Focus inspection shall be carried out Regularly for mobile aluminium Scaffolding | Daily activity schedule for each cluster / block / villa; and | Construction Manager Project Engineer OSH Manager | 2026-04-18 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00214 | 2026-04-16 | 16 | 2026-04 | 4 | Cluster 2A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Jackson | KEO | General |  | Scaffolding | YES | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 3 | 2 | 3 | 42 | 56% | 55.2% | NO | NO | Poor | YES | Poor supervision | 1. Lack of inspections 2. Inadequate supervision 3. Competency | All activities on the unasfe extended scaffolding has been suspended . All electrical cables crossing over the live traffic roads has been removed | Scaffolding inspection by competent scaffolding inspector cable management Subcontractor Management | Supervision deployment plan identifying the responsible site engineers, supervisors, and HSE personnel for each work front. | Construction Manager | 2026-04-18 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00215 | 2026-04-17 | 16 | 2026-04 | 2 | Cluster 7A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Liqat | Abdel Monem | KEO | General |  | Excavation | YES | 4 | 2.5 | 4 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 4.5 | 4 | 3 | 3 | 3 | 46 | 61.33% | 58.9% | YES | NO | Needs Improvement | YES | Poor supervision | PTW Failure Lack of Supervision No MSRA Implementation | Boundry wall excavation has been suspended. Instructed Action owners to take corrective and preventive action. | PTW procedure for excavation shall be implemented Regular trining sessions shall be carried out. Focus inspection shall be carried out for the boundry wall excavations |  | Cluster Construction Manager | 2026-04-20 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00216 | 2026-04-16 | 16 | 2026-04 | 2 | Cluster 8A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Jackson | KEO | General |  | Excavation | YES | 4 | 4 | 4 | 3 | 3.5 | 3 | 3.5 | 4 | 3 | 3.5 | 4 | 4 | 3 | 3 | 3 | 52.5 | 70% | 69.8% | NO | NO | Needs Improvement | YES | Poor supervision | PTW Failure Lack of Supervision No MSRA Implementation | Boundry wall excavation has been suspended. Instructed Action owners to take corrective and preventive action. | PTW procedure for excavation shall be implemented Regular trining sessions shall be carried out. Focus inspection shall be carried out for the boundry wall excavations |  | Construction Manager | 2026-04-20 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00217 | 2026-04-16 | 16 | 2026-04 | 2 | Cluster 8B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Javed | KEO | General |  | Edge Protection | YES | 2 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 3 | 4 | 3 | 4 | 2 | 3 | 4 | 47 | 62.67% | 59.8% | NO | NO | Needs Improvement | YES | Poor supervision | Inspection ,Monitoring and Compliance Lack of adequate supervision Inadequate competency | Activities suspended near to the leading edges where not adequately protected. | Focus inspections shall be carried out for the edge protections |  | Construction Manager Project Engineer OSH Manager | 2026-04-20 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00218 | 2026-04-17 | 16 | 2026-04 | 2 | Cluster 7B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur | Eyad | Abdel Monem | KEO | General |  | Scaffolding | YES | 4 | 4 | 3 | 4 | 3.5 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 56.5 | 75.33% | 76.4% | NO | YES | Good | NO | Inadequate competence | Lack of Subcontractor control Lack of supervision scaffolding inspection | Scaffolding unit re inspection required and communicated to the action owners. | Scaffolding shall be inspected by competent inspector based on the inspection regimen |  | Construction manager Project Engineer | 2026-04-21 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00221 | 2026-04-17 | 16 | 2026-04 | 4 | Cluster 1B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Hossam Ali Maher | Timur Terakopov | Md Ramadan / Osama Said | Jackson | KEO | General |  | Excavation | YES | 3.5 | 4 | 3.5 | 2 | 3.5 | 3 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 52.5 | 70% | 70.1% | NO | NO | Needs Improvement | YES | Poor supervision | PTW Failure Lack of Supervision No MSRA Implementation | Boundry wall excavation has been suspended. Instructed Action owners to take corrective and preventive action. | PTW procedure for excavation shall be implemented Regular trining sessions shall be carried out. Focus inspection shall be carried out for the boundry wall excavation |  | Construction manager HSE | 2026-04-21 | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00222 | 2026-04-18 | 16 | 2026-04 | 4 | Cluster 2B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Godwin & Abdel Monem | KEO | General | A/C duct installation from podium ladder & mobile scaffold | Work at Height | YES | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 1 |  | 3 | 2 | 2 | 3 | 0 | 3 | 32 | 42.67% | 45.2% | YES | NO | Poor | YES | Poor supervision | Lack of planning PTW failure Lack of Subcontractor control Lack of supervision No leadership presence | The unsafe work was stopped, demaged ladder decommisioned and workers removed from the site. The HSEM and site engineer of tghe main contractor were advised on safe preventive measures to take. | 1. Prepare Monthly lookahead programme for each package; 2. Prepare Weekly lookahead programme for each cluster; 3. Prepare Daily activity schedule for each cluster / block / villa 4. Develop Supervision deployment plan identifying the responsible site engineers, supervisors, and HSE personnel for each work front. 5. Ensure Subcontractors' engagement in the project is strictly based on the above plans. No work shall commence without an approved PTW by the main contractor. 6. Communicate officially to all subcontractors that no activity shall commence without first reporting to the main contractor on daily basis. 7. Regularly share the above plans with KEO for close follow up and monitoring. 8. Administer discipline to the key project leader(s) in the case of repeated violation. |  | Construction Manager | 2026-04-25 | See Asite reference
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00223 | 2026-04-18 | 16 | 2026-04 | 4 | Cluster 2C | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef | Godwin | KEO | General | Roof work from MEWP platform, buffing work, excavation works. | Excavation | YES | 4 | 4 | 3 | 3 |  | 2 | 4 | 4 |  | 2 | 2 |  | 3 | 2 | 2 | 35 | 46.67% | 47.6% | YES | NO | Poor | YES | Poor supervision | Lack of planning PTW failure Lack of Subcontractor control Lack of supervision No leadership presence | The unsafe work was stopped, demaged ladder decommisioned and workers removed from the site. The HSEM and site engineer of tghe main contractor were advised on safe preventive measures to take. | 1. Prepare Monthly lookahead programme for each package; 2. Prepare Weekly lookahead programme for each cluster; 3. Prepare Daily activity schedule for each cluster / block / villa 4. Develop Supervision deployment plan identifying the responsible site engineers, supervisors, and HSE personnel for each work front. 5. Ensure Subcontractors' engagement in the project is strictly based on the above plans. No work shall commence without an approved PTW by the main contractor. 6. Communicate officially to all subcontractors that no activity shall commence without first reporting to the main contractor on daily basis. 7. Regularly share the above plans with KEO for close follow up and monitoring. 8. Administer discipline to the key project leader(s) in the case of repeated violation. | Construction Manager | Construction Manager |  | See Asite reference
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00175 | 2026-04-18 | 16 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Shakir | KEO | v207 |  | Permit to Work | YES |  | 4 | 4 | 2 | 2 | 3 | 2 | 4 | 0 | 2 | 3 | 4 | 2 | 2 | 4 | 38 | 50.67% | 45% | YES | NO | Poor | YES | Poor supervision | • Poor Supervision • Inadequate Planning and Control • Weak Inspection, Monitoring, and Compliance | Unsafe conditions were addressed immediately, work was stopped where required, and the responsible supervision team was informed to implement corrective measures and restore compliance. | • Strengthen site supervision by ensuring competent supervisors are present at all times to monitor activities and enforce safe work practices. • Improve planning and control through comprehensive risk assessments, task planning, and strict adherence to approved procedures and MSRA. • Enhance inspection and monitoring by conducting regular site inspections, audits, and timely corrective actions for any non compliance. • Reinforce worker awareness via regular toolbox talks and targeted training to promote a strong safety culture and prevent recurrence. |  | Construction Manager | 2026-04-21 | See Asite reference
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00176 | 2026-04-18 | 16 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shakir | KEO | V15 |  | Edge Protection | NO |  | 4 | 3 |  | 4 | 3 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 45 | 60% | 55.4% | YES | NO | Needs Improvement | YES | Poor subcontractor control | • Poor Supervision • Inadequate Planning and Control • Weak Inspection, Monitoring, and Compliance | Unsafe conditions were addressed immediately, work was stopped where required, and the responsible supervision team was informed to implement corrective measures and restore compliance. | • Strengthen site supervision by ensuring competent supervisors are present at all times to monitor activities and enforce safe work practices. • Improve planning and control through comprehensive risk assessments, task planning, and strict adherence to approved procedures and MSRA. • Enhance inspection and monitoring by conducting regular site inspections, audits, and timely corrective actions for any non compliance. • Reinforce worker awareness via regular toolbox talks and targeted training to promote a strong safety culture and prevent recurrence. |  | Construction Manager | 2026-04-24 | See Asite reference
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00176 | 2026-04-20 | 17 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | Villa 77, store |  | Waste Management | NO | 3.5 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 4 | 4 | 56.5 | 75.33% | 75.4% | NO | YES | Good | YES | Poor supervision | Missing safety barricades and signage Poor housekeeping and material storage Unsafe high‑risk work control | supervisors were called, and rectification started immediately | Provide barricades, exclusion zones, and signage Maintain good housekeeping and safe storage Ensure close supervision and RAMS compliance |  | Construction Manager | 2026-04-23 | See Asite reference
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00178 | 2026-04-20 | 17 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shinoj M | KEO | Group 04 |  | Edge Protection | NO | 3 | 2 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 3 | 52 | 69.33% | 66.2% | NO | NO | Needs Improvement | YES | Poor supervision | 1. subcontractor control 2. Lack of maintenance crew 3. Housekeeping sysytem | Advised the engineer to allocate adequate resources to maintain the OHS standards | 1 conduct routine inspection 2. Competency assessment 3 Training and awareness |  | Construction manager HSE |  | A site reference provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-0224 | 2026-04-20 | 17 | 2026-04 | 4 | Cluster 2A | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Jackson | KEO | Villa 62,63,55,46 |  | Scaffolding | YES | 2 | 3 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 35 | 46.67% | 46.2% | YES | NO | Poor | YES | Poor supervision
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-0225 | 2026-04-20 | 17 | 2026-04 | 4 | Cluster 2B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | Godwin | KEO | Villa 132, 86,88 |  | Permit to Work | YES | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 4 | 0 | 3 | 34 | 45.33% | 43.6% | YES | NO | Poor | YES | PTW failure
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00179 | 2026-04-21 | 17 | 2026-04 | 3 | Cluster 5 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | 0 | Shinoj M | KEO | Block B |  | Electrical Safety | NO | 3 | 3 | 4 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | 3.5 | 4 | 4 | 4 | 2 | 52.5 | 70% | 68.1% | NO | NO | Needs Improvement | YES | Poor subcontractor control | 1 Inspection and maintenance 2 Housekeeping arrangements 3 Permit to work sysytem | Advised the engineer to allocate adequate resources to maintain the OHS standards | 1. Appoint a dedicated team for inspection an dmaintannace 2. Conduc t training to the workforce 3. Conduct periodic inspections |  | Construction manager HSE |  | A site reference provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00180 | 2026-04-21 | 17 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | S Samraj | KEO |  |  | Scaffolding | NO | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 51 | 68% | 66.4% | NO | NO | Needs Improvement | YES | Inadequate competence |  | Advised the engineer to allocate adequate resources to maintain the OHS standards
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00181 | 2026-04-21 | 17 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | V24,V44 |  | Electrical Safety | NO |  | 3 | 3 | 4 | 3 | 3.5 | 3.5 | 4 |  | 3.5 | 4 | 4 | 4 | 3.5 | 3.5 | 46.5 | 62% | 54.1% | YES | NO | Needs Improvement | NO | PTW failure | PTW Implementation-poor supervision-lack of subcontractor control | The construction manager has been informed and the concerned supervisory team was called to rectify all the observations raised in the inspection | Ensure PTW is implemented for all testing and commissioning activities,provide proper barricades prior starting any work on the slab of the parking |  | Construction Manager | 2026-04-28 | A site reference provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00182 | 2026-04-21 | 17 | 2026-04 | 3 | Cluster 3 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | 0 | Godwin | KEO |  |  | Work at Height | NO | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 42 | 56% | 55.8% | NO | NO | Poor | YES | Poor subcontractor control | Poor supervision Poor subcontractor control PTW failure | Workers were removed from the villa and the construction team advised to initiate immediate correction. Correcxtions include conducting general housekeeping around the affected villas, barricading exposed manhole, removing orange scaffolding from the villa and raising trailing cables from the floor. | 1. Install a door on the cat ladder 2. Control Access to cat ladder using PTW system. 3. Install temporary waste collection point at every villa. 4. Instruct contractors to conduct housekeeping by the end of every shift. 5. Work milestone and payment shall be linked to acceptable housekeeping standard. 6. PTW shall not be closed if housekeeping standard is poor. 7. New PTW shall not be issued if issues in previous permit are not resolved. |  | Construction Manager | 2026-04-24 | A site reference provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00183 | 2026-04-22 | 17 | 2026-04 | 3 | Cluster 6 | OK | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | 0 | Shakir | KEO | v03 |  | Excavation | NO |  | 4 | 4 | 3 |  | 4 | 4 | 4 |  | 2 | 3 | 4 | 3 | 3 | 4 | 42 | 56% | 48.2% | YES | NO | Poor | YES | PTW failure | poor supervisoin control-houseekping - material managment | site engineer was informed to ensure proper housekeeping and secure all the glass storage | -PTW implementation-proper subcontractor control |  | Construction Manager | 2026-04-29 | A site reference provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00184 | 2026-04-22 | 17 | 2026-04 | 3 | Cluster 4 | OK | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | 0 | Shinoj | KEO | Block 01 |  | Edge Protection |  | 4 | 2 | 2 | 3 | 3 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 52 | 69.33% | 67.8% | NO | NO | Needs Improvement | YES | Poor supervision | 1. Simultaneous operations 2. Lack of resources 3 Training and awareness | Advised the cluster engineer to allocate adequate resorces | 1- Conduct training for the workforce 2 Pre-plan the activities to avoid unsafe SIMOS 3 -conduct periodic inspections |  | CM OHS |  | A site reference provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00226 | 2026-04-21 | 17 | 2026-04 | 2 | Cluster 8B | OK | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur | Ahmad Adel | Jackson | KEO | VIlla 142 to 138 |  | Work at Height | YES | 1 | 2 | 2 | 2 | 3.5 | 2 | 2 | 3 | 3.5 | 3 | 2 | 4 | 2 | 3 | 3 | 38 | 50.67% | 48.4% | YES | NO | Poor
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00227
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00228
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00229
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00230
Formulas:
Week_No = IF([Inspection_Date]="","",WEEKNUM([Inspection_Date],2))

## Gap_Analysis
Gap Analysis
Use the control week and month to identify recurring gaps, weak KPIs and likely root causes. This supports weekly corrective and preventive action planning.
Selected Week No | 16
Selected Month (yyyy-mm) | 2026-04
KPI | Week Avg Score | Month Avg Score | Week Gap to 5 | Month Gap to 5 | Week Red Flags | Month Red Flags | Focus
Work at Height Control | 3.119 | 3.1017 | 1.881 | 1.8983 | 1 | 3 | Monitor
Edge Protection | 3.413 | 3.3333 | 1.587 | 1.6667 | 0 | 0 | Monitor
Falling Object Prevention | 3.3696 | 3.3095 | 1.6304 | 1.6905 | 0 | 3 | Monitor
Excavation Safety | 2.6818 | 2.9224 | 2.3182 | 2.0776 | 3 | 4 | Monitor
Scaffolding Compliance | 3.1364 | 3.2083 | 1.8636 | 1.7917 | 0 | 0 | Monitor
PTW Implementation | 2.5652 | 2.8254 | 2.4348 | 2.1746 | 3 | 6 | Monitor
PTW Field Verification | 2.6739 | 2.754 | 2.3261 | 2.246 | 3 | 8 | Monitor
MSRA Quality | 3.5217 | 3.619 | 1.4783 | 1.381 | 1 | 1 | Monitor
Lifting/Precast Installation | 3.1765 | 3.2736 | 1.8235 | 1.7264 | 1 | 2 | Monitor
Traffic & Man-Machine Interface | 3.1304 | 3.1984 | 1.8696 | 1.8016 | 0 | 2 | Monitor
Housekeeping/Waste Management | 3.0652 | 3.1825 | 1.9348 | 1.8175 | 1 | 1 | Monitor
Welfare Arrangement | 3.6818 | 3.7823 | 1.3182 | 1.2177 | 1 | 1 | Monitor
Fire Readiness | 3.1087 | 3.2143 | 1.8913 | 1.7857 | 0 | 0 | Monitor
Supervision & Subcontractor Control | 2.6739 | 2.9286 | 2.3261 | 2.0714 | 3 | 5 | Monitor
Temporary Electrical & Tool Safety | 3.1957 | 3.1349 | 1.8043 | 1.8651 | 1 | 1 | Monitor
Root Cause | Week Count | Month Count | Comment
Leadership failure | 0 | 0
Poor supervision | 14 | 31
Poor planning | 1 | 4
PTW failure | 4 | 8
Weak MSRA | 0 | 0
Poor subcontractor control | 1 | 13
Resource constraint | 0 | 0
Inadequate competence | 2 | 5
Poor housekeeping culture | 0 | 0
Interface / simultaneous activity conflict | 0 | 0
Other | 1 | 1

## Weekly_Dashboard
Weekly Dashboard
Set the control week and month in blue-font cells. This sheet summarizes weekly and current month performance by cluster and highlights weak KPIs / root causes.
Control inputs
Selected Week No | 17
Selected Month (yyyy-mm) | 2026-04
Previous Month (yyyy-mm) | 2026-03
Cluster | Package | Contractor | Week Avg Raw % | Week Avg Weighted % | Week Red Flags | Month Avg Raw % | Month Avg Weighted % | Month Red Flags | Month Improvement | Award Eligible | Rank
Cluster 7A | 2 | TAJV |  |  | 0 | 62.27% |  | 1 |  | NO | 10
Cluster 7B | 2 | TAJV |  |  | 0 | 72% |  | 0 |  | NO | 2
Cluster 8A | 2 | TAJV |  |  | 0 | 65.11% | 64.23% | 0 | -17.23% | NO | 8
Cluster 8B | 2 | TAJV | 50.67% | 48.4% | 1 | 61.33% | 60.2% | 1 |  | NO | 11
Cluster 8C | 2 | TAJV |  |  | 0 | 68.89% | 67.77% | 0 |  | NO | 3
Cluster 8D | 2 | TAJV |  |  | 0 | 68% | 67.1% | 0 |  | NO | 4
Cluster 3 | 3 | INNOVO | 56% | 55.8% | 0 | 58.48% | 56.74% | 2 |  | NO | 12
Cluster 4 | 3 | INNOVO | 68.67% | 68.67% | 0 | 65.58% |  | 1 |  | NO | 7
Cluster 5 | 3 | INNOVO | 69.67% | 67.15% | 0 | 62.86% | 61.27% | 3 |  | NO | 9
Cluster 6 | 3 | INNOVO | 64.44% | 59.23% | 2 | 66.67% | 64.04% | 5 |  | NO | 6
Cluster 1A | 4 | TAJV |  |  | 0 | 67.33% | 66.55% | 0 |  | NO | 5
Cluster 1B | 4 | TAJV |  |  | 0 | 74% | 74.3% | 0 |  | NO | 1
Cluster 2A | 4 | TAJV | 46.67% | 46.2% | 1 | 55.17% | 53.75% | 1 |  | NO | 13
Cluster 2B | 4 | TAJV | 45.33% | 43.6% | 1 | 49.5% | 48.2% | 3 |  | NO | 14
Cluster 2C | 4 | TAJV |  |  | 0 | 45.78% | 46.83% | 3 | 18.39% | NO | 15
KPI performance snapshot
KPI | Selected Week Avg Score | Selected Month Avg Score | Gap to 5 (Week) | Gap to 5 (Month) |  | Root Cause | Selected Week Count | Selected Month Count
Work at Height Control | 2.3889 | 3.1017 | 2.6111 | 1.8983 |  | Leadership failure | 0 | 0
Edge Protection | 3 | 3.3333 | 2 | 1.6667 |  | Poor supervision | 4 | 31
Falling Object Prevention | 3.0909 | 3.3095 | 1.9091 | 1.6905 |  | Poor planning | 0 | 4
Excavation Safety | 3.0909 | 2.9224 | 1.9091 | 2.0776 |  | PTW failure | 3 | 8
Scaffolding Compliance | 3.15 | 3.2083 | 1.85 | 1.7917 |  | Weak MSRA | 0 | 0
PTW Implementation | 2.9545 | 2.8254 | 2.0455 | 2.1746 |  | Poor subcontractor control | 2 | 13
PTW Field Verification | 2.7727 | 2.754 | 2.2273 | 2.246 |  | Resource constraint | 0 | 0
MSRA Quality | 3.5455 | 3.619 | 1.4545 | 1.381 |  | Inadequate competence | 1 | 5
Lifting/Precast Installation | 3.3889 | 3.2736 | 1.6111 | 1.7264 |  | Poor housekeeping culture | 0 | 0
Traffic & Man-Machine Interface | 3.1364 | 3.1984 | 1.8636 | 1.8016 |  | Interface / simultaneous activity conflict | 0 | 0
Housekeeping/Waste Management | 3.1364 | 3.1825 | 1.8636 | 1.8175 |  | Other | 0 | 1
Welfare Arrangement | 3.7273 | 3.7823 | 1.2727 | 1.2177
Fire Readiness | 3.4545 | 3.2143 | 1.5455 | 1.7857
Supervision & Subcontractor Control | 3.0455 | 2.9286 | 1.9545 | 2.0714
Temporary Electrical & Tool Safety | 3.0455 | 3.1349 | 1.9545 | 1.8651

## Monthly_Dashboard
Monthly Dashboard
Set the selected month and previous month in blue-font cells. Use this view for monthly recognition and improvement review.
Selected Month (yyyy-mm) | 2026-04
Previous Month (yyyy-mm) | 2026-03
Cluster | Package | Contractor | Month Avg Raw % | Month Avg Weighted % | Red Flags | Improvement vs Prev Month | Award Eligible | Rank | Open Actions | Overdue Actions
Cluster 7A | 2 | TAJV | 62.27% |  | 1 |  | NO | 10 | 3 | 3
Cluster 7B | 2 | TAJV | 72% |  | 0 |  | NO | 2 | 1 | 1
Cluster 8A | 2 | TAJV | 65.11% | 64.23% | 0 | -17.23% | NO | 8 | 1 | 0
Cluster 8B | 2 | TAJV | 61.33% | 60.2% | 1 |  | NO | 11 | 0 | 0
Cluster 8C | 2 | TAJV | 68.89% | 67.77% | 0 |  | NO | 3 | 1 | 1
Cluster 8D | 2 | TAJV | 68% | 67.1% | 0 |  | NO | 4 | 1 | 1
Cluster 3 | 3 | INNOVO | 58.48% | 56.74% | 2 |  | NO | 12 | 2 | 2
Cluster 4 | 3 | INNOVO | 65.58% |  | 1 |  | NO | 7 | 2 | 2
Cluster 5 | 3 | INNOVO | 62.86% | 61.27% | 3 |  | NO | 9 | 2 | 2
Cluster 6 | 3 | INNOVO | 66.67% | 64.04% | 5 |  | NO | 6 | 3 | 3
Cluster 1A | 4 | TAJV | 67.33% | 66.55% | 0 |  | NO | 5 | 1 | 1
Cluster 1B | 4 | TAJV | 74% | 74.3% | 0 |  | NO | 1 | 1 | 1
Cluster 2A | 4 | TAJV | 55.17% | 53.75% | 1 |  | NO | 13 | 0 | 0
Cluster 2B | 4 | TAJV | 49.5% | 48.2% | 3 |  | NO | 14 | 0 | 0
Cluster 2C | 4 | TAJV | 45.78% | 46.83% | 3 | 18.39% | NO | 15 | 1 | 1

## CAPA_Tracker
Corrective and Preventive Action (CAPA) Tracker
Automated from Weekly_Inspections. Each inspection row with a recorded gap/action appears here automatically. Close Date can be updated manually if you want to mark an action closed.
Action_ID | Date_Raised | Package | Cluster | Contractor | KPI_Area | Finding | Root_Cause | Immediate_Action | Preventive_Action | Action_Owner | Target_Date | Status | Close_Date | Days_Open | Overdue_Flag | Evidence_Link
20260326-Cluster2C-01-A1 | 2026-03-26 | 4 | Cluster 2C | TAJV | Work at Height | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Leadership failure | Unsafe work practices were suspended immediately. The CM of the cluster was called but he refused to visit the location. | 1. PTW must be controlled by the main contractor. 2. Close supervision of sub-contractors by main contractor shall be ensured. 3. Non-performing subcontractors shall not be paid and shall be removed from project. 4. Non-performing construction team shall be replaced without delays | 1-3rd recommendation by the cluster CM 4th recommendation by the PD. | 2026-04-02 | Open |  | 27 | YES | 0
20260326-Cluster8A-01-A1 | 2026-03-26 | 2 | Cluster 8A | TAJV | Scaffolding | No significant gap observed | Other | The team was commended for their visible leadership in driving transformation at Cluster 8A. | The Construction Manager and his team were advised to ensure that sub-contractors do not mess up with their site. The following advise was given: 1. No payment for work if site condition is below the acceptable standard. 2. Close supervision of sub-contractors by the construction team of the main contractor. 3. Housekeeping shall be maintined for all shift. 4. Provide a temporary storage area for waste for each villa. 5. PTW shall remain under the control of the main contractor. | Construction Manager of Cluster 8A HSE Manager of TAJV | Always | Open |  | 27 | NO | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00158-A1 | 2026-04-03 | 3 | Cluster 4 | INNOVO | Edge Protection | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Poor supervision | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection | Construction Manager Cluster 04 | 2026-04-10 | Open |  | 19 | YES | uploaded on Asite
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00159-A1 | 2026-04-04 | 3 | Cluster 5 | INNOVO | Edge Protection | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Poor subcontractor control | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection | Construciton manager | 2026-04-09 | Open |  | 18 | YES | Upload on Asite
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00160-A1 | 2026-04-04 | 3 | Cluster 6 | INNOVO | Edge Protection | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Poor supervision | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection | Construction Manager | 2026-04-11 | Open |  | 18 | YES | uploaded on Asite
20260403-Cluster3-01-A1 | 2026-04-03 | 3 | Cluster 3 | INNOVO | Edge Protection | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control | Poor planning | stopped the unsafe activities , called the area engineer to the location discuss about the corrective and preventive actions | conduct coordination meetings , provide adequate facilities for waste collection | Project engineer construction manager | 0 | Open |  | 19 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00196-A1 | 2026-04-02 | 2 | Cluster 7A | TAJV | Edge Protection | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Poor supervision | All activities inside the visited villa have been suspened and corrective and preventive actions required have been communicated with action owners . | Provide competent supervsion to ensure the activities inline with OSH requirements and proeprly managing the subcontractor. | Project engineer construction manager | 2026-04-09 | Open |  | 20 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00161-A1 | 2026-04-06 | 3 | Cluster 3 | INNOVO | Traffic Management | 1. Poor coordination 2. Poor sub-contractor control 4. PTW failure | Poor planning | 1. Maintain the pedestrian access 2. Reinstate the barricades 3. Provide access to the villas 4.Apoint competent scaffolding crew | 1. Preplan the activities 2. Conduct a week's look-ahead planning to avoid conflicts 3. Conduct training for the involved teams 4. Evaluate the competency of the scaffolding crew | Construction manager Project Engineer HSE officer | 0 | Open |  | 16 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00197-A1 | 2026-04-02 | 2 | Cluster 7B | TAJV | Work at Height | 1. Poor sub-contractor control | Poor subcontractor control | Cordination Meeting conducted | Sub contractor shall be managed based on the project OSH Requirements | Project engineer construction manager | 2026-04-09 | Open |  | 20 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00198-A1 | 2026-04-03 | 2 | Cluster 8C | TAJV | Scaffolding | Inadequate comptence | Inadequate competence | Coordination Meeting conducted | Regular Training sessions shall be carried out | 0 | 2026-04-10 | Open |  | 19 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00198-A1 | 2026-04-03 | 2 | Cluster 8D | TAJV | Electrical Safety | Poor supervision | Poor supervision | Coordination Meeting conducted | Regular scaffolding and Distribution Board inspection | 0 | 2026-04-10 | Open |  | 19 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00199-A1 | 2026-04-06 | 4 | Cluster 1A | TAJV | Scaffolding | Poor subcontractor control | Poor subcontractor control | Unsafe work has been suspended | Regular scaffolding and Distribution Board inspection | 0 | 2026-04-12 | Open |  | 16 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00200-A1 | 2026-04-06 | 4 | Cluster 1B | TAJV | Scaffolding | Poor subcontractor control | Poor subcontractor control | Coordination Meeting conducted | Regular scaffolding and Distribution Board inspection | 0 | 2026-04-12 | Open |  | 16 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00162-A1 | 2026-04-06 | 3 | Cluster 4 | INNOVO | Lifting Operations | • HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Poor supervision | • Unsafe activities were stopped immediately. • Housekeeping, waste removal, and access rectification started | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. | Construction manager Project Engineer | 2026-04-10 | Open |  | 16 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-WR-HS-75-A1 | 2026-04-07 | 3 | Cluster 5 | INNOVO | Fire Readiness | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | PTW failure | unsafe blocks observed in walk fixed away from edge | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. | Construction manager Project Engineer | 2026-04-14 | Open |  | 15 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-WR-HS-75-A1 | 2026-04-07 | 3 | Cluster 6 | INNOVO | Electrical Safety | •HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Poor subcontractor control | permit to work verification done on site.edge protection team was called to fix the edge protection and excavation barricades | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs. | Construction Manager | 2026-04-14 | Open |  | 15 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00201-A1 | 2026-04-07 | 2 | Cluster 7A | TAJV | Falling Objects | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Poor supervision | edge protection team was called to fix the edge protection and excavation barricades | Enforce strict supervision and permit compliance. Implement proper planning, housekeeping, and waste management systems. Conduct regular inspections, training, and safety awareness programs | Construction manager Project Engineer | 2026-04-12 | Open |  | 15 | YES | Asite Reff provided
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00202-A1 | 2026-04-07 | 2 | Cluster 7A | TAJV | Edge Protection | •HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Poor supervision | Instructed contractor to reverify all scaffolding | Competent scaffolding inspector shall be inspected all scaffolding units | Construction manager Project Engineer | 2026-04-12 | Open |  | 15 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00164-A1 | 2026-04-08 | 3 | Cluster 6 | INNOVO | Excavation | HSE Management System Implementation • Planning and Control • Inspection, Monitoring, and Compliance | Poor supervision | Worker removed from the villa in adequate access and edge protection | • Enforce strict supervision and permit compliance. • Implement proper planning, housekeeping, and waste management systems. • Conduct regular inspections, training, and safety awareness programs. • Access should always be well-maintained and inspected by a competent person • Permit to work should only be issued if the villa is safe to work in | Construction manager Project Engineer | 2026-04-15 | Open |  | 14 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00163-A1 | 2026-04-08 | 0 |  |  |  |  | Poor subcontractor control | 1. Worker removed from the villa 2. safe access provided by the contractor 3. allocated people fro material arrangements | 1. Conduct training and awareness on the site supervision level 2. Conduct routine inspections 3. | 1. Project engineer 2. Construction Manager 3. OHS offcer | 0 | Open |  | 14 | YES | Asite Reff provided
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00165-A1
SIDP3-BW-KEO-ZZ-ZZ-XX-RP-HS-00166-A1
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00203-A1
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00204-A1
SIDPW-BW-KEO-ZZ-ZZ-XX-RP-HS-00205-A1
Formulas:
Date_Raised = Weekly_Inspections!$[Date_Raised]
Date_Raised = Weekly_Inspections!$[Date_Raised, row above]
Days_Open = IF([Date_Raised]="","",IF([Status]="Closed",IF([Close_Date]="","",[Close_Date]-[Date_Raised]),TODAY()-[Date_Raised]))
Overdue_Flag = IF(OR([Date_Raised]="",[Target_Date]="",[Status]="Closed"),"",IF(TODAY()>[Target_Date],"YES","NO"))

## April
April 2026 ¦ 09:00-11:00 ¦ 3 Simultaneous Site Walk Groups
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Attendance / Status
|  | 01 Apr 2026 | 02 Apr 2026 | 03 Apr 2026 | 04 Apr 2026
|  | 09-10 ¦ G1 ¦ Cluster 8A | 09-10 ¦ G1 ¦ Cluster 7A | 09-10 ¦ G1 ¦ Cluster 8C | 09-10 ¦ G1 ¦ Cluster 7B
|  | 09-10 ¦ G2 ¦ Cluster 8B | 09-10 ¦ G2 ¦ Cluster 7B | 09-10 ¦ G2 ¦ Cluster 8D | 09-10 ¦ G2 ¦ Cluster 8A
|  | 09-10 ¦ G3 ¦ Cluster 5 | 09-10 ¦ G3 ¦ Cluster 8A | 09-10 ¦ G3 ¦ Cluster 3 | 09-10 ¦ G3 ¦ Cluster 5
|  | 10-11 ¦ G1 ¦ Cluster 6 | 10-11 ¦ G1 ¦ Cluster 1A | 10-11 ¦ G1 ¦ Cluster 4 | 10-11 ¦ G1 ¦ Cluster 6
|  | 10-11 ¦ G2 ¦ Cluster 2A | 10-11 ¦ G2 ¦ Cluster 1B | 10-11 ¦ G2 ¦ Cluster 2C | 10-11 ¦ G2 ¦ Cluster 1B
|  | 10-11 ¦ G3 ¦ Cluster 2B | 10-11 ¦ G3 ¦ Cluster 2A | 10-11 ¦ G3 ¦ Cluster 1A | 10-11 ¦ G3 ¦ Cluster 2A
Cluster CM Attended
Cluster Engineers + Supervision team attended
Cluster HSE Attended
06 Apr 2026 | 07 Apr 2026 | 08 Apr 2026 | 09 Apr 2026 | 10 Apr 2026 | 11 Apr 2026
09-10 ¦ G1 ¦ Cluster 7A | 09-10 ¦ G1 ¦ Cluster 3 | 09-10 ¦ G1 ¦ Cluster 8B | 09-10 ¦ G1 ¦ Cluster 7B | 09-10 ¦ G1 ¦ Cluster 8D | 09-10 ¦ G1 ¦ Cluster 8A
09-10 ¦ G2 ¦ Cluster 7B | 09-10 ¦ G2 ¦ Cluster 4 | 09-10 ¦ G2 ¦ Cluster 8C | 09-10 ¦ G2 ¦ Cluster 8A | 09-10 ¦ G2 ¦ Cluster 7A | 09-10 ¦ G2 ¦ Cluster 8B
09-10 ¦ G3 ¦ Cluster 3 | 09-10 ¦ G3 ¦ Cluster 5 | 09-10 ¦ G3 ¦ Cluster 6 | 09-10 ¦ G3 ¦ Cluster 8B | 09-10 ¦ G3 ¦ Cluster 4 | 09-10 ¦ G3 ¦ Cluster 6
10-11 ¦ G1 ¦ Cluster 4 | 10-11 ¦ G1 ¦ Cluster 6 | 10-11 ¦ G1 ¦ Cluster 3 | 10-11 ¦ G1 ¦ Cluster 1B | 10-11 ¦ G1 ¦ Cluster 5 | 10-11 ¦ G1 ¦ Cluster 3
10-11 ¦ G2 ¦ Cluster 1A | 10-11 ¦ G2 ¦ Cluster 3 | 10-11 ¦ G2 ¦ Cluster 2B | 10-11 ¦ G2 ¦ Cluster 2A | 10-11 ¦ G2 ¦ Cluster 1A | 10-11 ¦ G2 ¦ Cluster 2A
10-11 ¦ G3 ¦ Cluster 1B | 10-11 ¦ G3 ¦ Cluster 4 | 10-11 ¦ G3 ¦ Cluster 2C | 10-11 ¦ G3 ¦ Cluster 2B | 10-11 ¦ G3 ¦ Cluster 1B | 10-11 ¦ G3 ¦ Cluster 2B
Cluster CM Attended
Cluster Engineers + Supervision team attended
Cluster HSE Attended
13 Apr 2026 | 14 Apr 2026 | 15 Apr 2026 | 16 Apr 2026 | 17 Apr 2026 | 18 Apr 2026
09-10 ¦ G1 ¦ Cluster 7B | 09-10 ¦ G1 ¦ Cluster 4 | 09-10 ¦ G1 ¦ Cluster 8C | 09-10 ¦ G1 ¦ Cluster 8A | 09-10 ¦ G1 ¦ Cluster 7A | 09-10 ¦ G1 ¦ Cluster 8B
09-10 ¦ G2 ¦ Cluster 8A | 09-10 ¦ G2 ¦ Cluster 5 | 09-10 ¦ G2 ¦ Cluster 8D | 09-10 ¦ G2 ¦ Cluster 8B | 09-10 ¦ G2 ¦ Cluster 7B | 09-10 ¦ G2 ¦ Cluster 8C
09-10 ¦ G3 ¦ Cluster 4 | 09-10 ¦ G3 ¦ Cluster 6 | 09-10 ¦ G3 ¦ Cluster 3 | 09-10 ¦ G3 ¦ Cluster 8C | 09-10 ¦ G3 ¦ Cluster 5 | 09-10 ¦ G3 ¦ Cluster 3
10-11 ¦ G1 ¦ Cluster 5 | 10-11 ¦ G1 ¦ Cluster 3 | 10-11 ¦ G1 ¦ Cluster 4 | 10-11 ¦ G1 ¦ Cluster 2A | 10-11 ¦ G1 ¦ Cluster 6 | 10-11 ¦ G1 ¦ Cluster 4
10-11 ¦ G2 ¦ Cluster 1B | 10-11 ¦ G2 ¦ Cluster 4 | 10-11 ¦ G2 ¦ Cluster 2C | 10-11 ¦ G2 ¦ Cluster 2B | 10-11 ¦ G2 ¦ Cluster 1B | 10-11 ¦ G2 ¦ Cluster 2B
10-11 ¦ G3 ¦ Cluster 2A | 10-11 ¦ G3 ¦ Cluster 5 | 10-11 ¦ G3 ¦ Cluster 1A | 10-11 ¦ G3 ¦ Cluster 2C | 10-11 ¦ G3 ¦ Cluster 2A | 10-11 ¦ G3 ¦ Cluster 2C
Cluster CM Attended
Cluster Engineers + Supervision team attended
Cluster HSE Attended
20 Apr 2026 | 21 Apr 2026 | 22 Apr 2026 | 23 Apr 2026 | 24 Apr 2026 | 25 Apr 2026
09-10 ¦ G1 ¦ Cluster 8A | 09-10 ¦ G1 ¦ Cluster 5 | 09-10 ¦ G1 ¦ Cluster 8D | 09-10 ¦ G1 ¦ Cluster 8B | 09-10 ¦ G1 ¦ Cluster 7B | 09-10 ¦ G1 ¦ Cluster 8C
09-10 ¦ G2 ¦ Cluster 8B | 09-10 ¦ G2 ¦ Cluster 6 | 09-10 ¦ G2 ¦ Cluster 7A | 09-10 ¦ G2 ¦ Cluster 8C | 09-10 ¦ G2 ¦ Cluster 8A | 09-10 ¦ G2 ¦ Cluster 8D
09-10 ¦ G3 ¦ Cluster 5 | 09-10 ¦ G3 ¦ Cluster 3 | 09-10 ¦ G3 ¦ Cluster 4 | 09-10 ¦ G3 ¦ Cluster 8D | 09-10 ¦ G3 ¦ Cluster 6 | 09-10 ¦ G3 ¦ Cluster 4
10-11 ¦ G1 ¦ Cluster 6 | 10-11 ¦ G1 ¦ Cluster 4 | 10-11 ¦ G1 ¦ Cluster 5 | 10-11 ¦ G1 ¦ Cluster 2B | 10-11 ¦ G1 ¦ Cluster 3 | 10-11 ¦ G1 ¦ Cluster 5
10-11 ¦ G2 ¦ Cluster 2A | 10-11 ¦ G2 ¦ Cluster 5 | 10-11 ¦ G2 ¦ Cluster 1A | 10-11 ¦ G2 ¦ Cluster 2C | 10-11 ¦ G2 ¦ Cluster 2A | 10-11 ¦ G2 ¦ Cluster 2C
10-11 ¦ G3 ¦ Cluster 2B | 10-11 ¦ G3 ¦ Cluster 6 | 10-11 ¦ G3 ¦ Cluster 1B | 10-11 ¦ G3 ¦ Cluster 1A | 10-11 ¦ G3 ¦ Cluster 2B | 10-11 ¦ G3 ¦ Cluster 1A
Cluster CM Attended
Cluster Engineers + Supervision team attended
Cluster HSE Attended
27 Apr 2026 | 28 Apr 2026 | 29 Apr 2026 | 30 Apr 2026
09-10 ¦ G1 ¦ Cluster 8B | 09-10 ¦ G1 ¦ Cluster 6 | 09-10 ¦ G1 ¦ Cluster 7A | 09-10 ¦ G1 ¦ Cluster 8C
09-10 ¦ G2 ¦ Cluster 8C | 09-10 ¦ G2 ¦ Cluster 3 | 09-10 ¦ G2 ¦ Cluster 7B | 09-10 ¦ G2 ¦ Cluster 8D
09-10 ¦ G3 ¦ Cluster 6 | 09-10 ¦ G3 ¦ Cluster 4 | 09-10 ¦ G3 ¦ Cluster 5 | 09-10 ¦ G3 ¦ Cluster 7A
10-11 ¦ G1 ¦ Cluster 3 | 10-11 ¦ G1 ¦ Cluster 5 | 10-11 ¦ G1 ¦ Cluster 6 | 10-11 ¦ G1 ¦ Cluster 2C
10-11 ¦ G2 ¦ Cluster 2B | 10-11 ¦ G2 ¦ Cluster 6 | 10-11 ¦ G2 ¦ Cluster 1B | 10-11 ¦ G2 ¦ Cluster 1A
10-11 ¦ G3 ¦ Cluster 2C | 10-11 ¦ G3 ¦ Cluster 3 | 10-11 ¦ G3 ¦ Cluster 2A | 10-11 ¦ G3 ¦ Cluster 1B
Cluster CM Attended
Cluster Engineers + Supervision team attended
Cluster HSE Attended
Tuesday = Package 3 only ¦ Thursday = Package 2 & 4 only ¦ Other days = mixed packages